## Sheet1
Bump Chart for Family F Head Restraints Updated on 12/04/06 by John Orzelski | [6 empty] | Engineer(s) |  |  |  |  | J. Kaminski | Orzelski | Orzelski | Orzelski | Trowbridge | Orzelski
PAD / MAD
PPAP Date
[7 empty] | Coordinated Change (Y/N) | [9 empty] | Y
[7 empty] | Status (R, A, W, I) | [5 empty] | R | R | A
[7 empty] | Brief Concern Description ---> |  |  |  | Insert Next Concern Beyond The Column | NB00-E-11870842-000 C170 Release per core change C11853349 | Delete HR strap and add EPP | Minor shape change of EPP insert | Revise EPP (add depression at top and increase retention). Revise tube form to shift EPP forward and up. Update PU foam volumes and density for all programs. | P-release of D471 HR asy. 8A83-96610A60-AA 10/9/2006. | Shift EPP position 5mm forward by revising armature shape. Extend HR armature posts by 10mm per side, move lower notches down 10mm(master), 10.3mm (slave) and middle notches 5mm down. Revise shape of 2 lower notches for 550N vertical retention. Increase height of EPP by 5mm, revise trench and surfaces. | D385, D471, P415 only: Styling change and 2 new EPPs for IIHS GOOD rating and 202a gap. EPP suffix D for D385 only, suffix E for D471 and P415.
[7 empty] | Concern # |  |  |  |  | C11870842 | C11853349 | C11879014 | AB00-E-11898654-000 | NB00-E-11874467-083 | C11930857 | C11950154
|  | PART NUMBER |  |  |  |  | Notice #
Component/JIT End Item | Design Area | PFX | BASE |  | SUF (REF) | PART DESCRIPTION | Released | PM Auth | Working | Invest
[7 empty] | R | A | W | I
C | Head Restraint | 8U5A | 96 | 610A44 | A* | H/Restr. Tube Form | AD | [7 empty] | AC |  | AD
C | Head Restraint | 8U5A | 96 | 611E46 | C* | EPP Insert | CC | [5 empty] | CA | CA | CB |  | CC
[5 empty] | D* | EPP Insert (C170 and D385) |  | DA | [9 empty] | DA
[5 empty] | E* | EPP Insert |  | EA | [9 empty] | EA
C | Head Restraint | 8U5A | 96 | 61172 | A* | Rod and EPP assy for C170 only (tube + EPP suffic C) | AD | [5 empty] | AB | AB | AC |  | AD
[5 empty] | B* | Rod and EPP assy for D385 only (tube + EPP suffic D) |  | BA | [9 empty] | BA
[5 empty] | C* | Rod and EPP assy for D471 and P415 (tube + EPP suffic E) |  | CA | [9 empty] | CA
E | Head Restraint | 9L34 | 96 | 610A60 | A* | Head Restraint Assembly - Adjustable (P415) | A0 |  |  | AA |  | 9L3A-96610A60-A0 is in WERS. Will change to 9L34. Not P-released yet
E | Head Restraint | 8S43 | 54 | 610A60 | A* | Head Restraint Assembly - Adjustable (C170) | AC | AD |  |  |  | AB |  |  | AC |  | AD
E | Head Restraint | 8A53 | 96 | 610A60 | A | Head Restraint Assembly - Adjustable (D385 / E386 Lo Series) | DISCONTINUED
E | Head Restraint | 8A53 | 54 | 610A60 | B* | Head Restraint Assembly - Adjustable (D385) | B1 | BB | [8 empty] | BB
E | Head Restraint | 8A83 | 96 | 610A60 | A* | Head Restraint Assembly - Adjustable (D471) | AA | To be replaced by 74610A60-AB | [7 empty] | AA
E | Head Restraint | 8A83 | 74 | 610A60 | A* | Head Restraint Assembly - Adjustable (D471) |  |  | AB |  |  | Base part number 96... to be replaced by 74... |  |  |  |  | AB
no release plans | Head Restraint |  |  | TBD |  | Rod and Strap Asy - Head Restraint Fixed
Notes:
1. Head Restraint Assemblies XXX-XX610A60-XX are released by programs.
2. C170 "AE" Level Concern (#C11961975) not posted on this bump chart. Engineering change to A-surface-to pass 202A gap requirement and close-out trench only. No foam tool has been kicked off from Ford that represents these changes. (M. Vecera)