## Sheet1
Component | Status | Next steps | Champion
4-way headrest | OK to Tool at current level | 1. Lear engineering to send OK to Tool email to Windsor Machine and Irvin referencing ECN. | L. Swikoski
|  | 2. Windsor machine to provide samples to Arlington this weekend with (2) proposals; closeout changing from 6mm to 3mm, and button hole increasing diameter by 2mm. | L. Bilbrey
2-way 1st row headrests | OK to Tool at current level, both cloth and leather. | 1. Irvin to provide Lear with 5 step on cloth french seam chatter issue. | B. Collier
|  | 2. Lear engineering to send OK to Tool email referencing latest level ECN's | L. Swikoski
|  | 3. Lear to follow up with GM, Foamex, & Milliken regarding construction approvals with A300 laminations to Bolster cloth (6mm) , WN1J & WN1Y vinyl (3mm). | M. Reinhold
|  | 4. Irvin to provide timing for ETR/PTR samples with laminated cloth, and vinyl with similated lamination. | R. James
2nd row headrests | Not production approved. Current builds will continue to support with the AA02 level (larger opening) | 1. Irvin & Bing to coordinate 10 pc. (of each, cloth and vinyl) PTR at the new AA03 level with the forward closeout seam moved rearward. This is hot due to the poor execution on the AA02 level. Irvin to get PTR samples into Arlington for further review and buyoff. | N. Spiekout
|  | 2. Follow up with lamination samples. | Team; Lear/Bing/Irvin
|  | 3. Irvin to provide laminated samples once new level trim is bought off. | N. Spiekout
|  | 4. Lear engineering sign off for OK to Tool & ECN. | M. Wright
2nd row AL4 armrests | Not production approved. Builds will continue to support at current level. | 1. Irvin and JL to coordinate ETR samples to closeout execution | N. Spiekout
|  | 2. OK to Tool pending PTR samples. Lear engineering buy off & OK to Tool ECN. | M. Wright
|  | 3. Breakpoint new level. | Team; Lear/JL/Irvin
2nd row AM8 armrests | Cloth is OK to Tool, leather & vinyl still pending. Builds will continue to support at current level | 1. Lear engineering to send OK to Tool email to Mendon & Irvin for cloth armrests only. - DONE | M. Wright
|  | 2. Irvin to provide timing for multiple iterations of samples. | B. Collier
|  | 3. Irvin & Mendon to coordinate ETR at Mendon off Lear approved sample design. | B. Collier/P. Westerman
|  | 4. Lear to ensure materials used for samples are construction approved with customer. | M. Reinhold
|  | 5. Irvin & Mendon to run PTR samples and ship to Arlington for further review and buyoff. | B. Collier/P. Westerman
|  | 6. Lear engineering buy off & OK to Tool ECN. | M. Wright
|  | 7. Breakpoint new level. | Team; Lear program management/Lear Mendon/ Irvin
3rd row headrests (Domestic & Export) | Ok to Tool at current level. | 1. Lear engineering to send OK to Tool email to Bing and Irvin referencing ECN's | D. Solak or L. Freeman
|  | 2. Follow up with new lamination samples for Domestic. | Team; Lear/Bing/Irvin

## Readiness Review
| Supplier Readiness Review |  |  |  |  | 2005-10-08
Open Issues Matrix
Item # | Section | Issue | Next steps | Expected Date of Completion | Actual Completion date | Champion
1 | Launch Management | Run at rate have not been completed due to not enough components to build at once and a ship as you build schedule | Plan run at rate for 10-17-05 shoot to 100% if components are received where we can build min. of 2 hours at 84 pcs per hour. | 2005-10-18 |  | Lisa Bilbrey/ Lisa Legras
2 | Industrial Engineering | Only estimated Labor standards have been establish based on to not enough builds. | Establish & confirm labor standards at the 100% run at rate. | 2005-10-18 |  | Lisa Bilbrey/ Lisa Legras
3 | Industrial Engineering | Safety PSR's need to be completed | Schedule PSR's on all equipment | 2005-10-14 |  | Lisa Legras
4 | Logistics | Releases not being received by any of the plant to review for volume mix at each location and for each program | Work with Customers to resolve issues | 2005-10-14 |  | Lisa Legras
5 | Logistics | Our final asm & our Supplier banks need to be confirmed and compare with release requirements | Set up our safety stock & supplier bank requirements when we receive Releases | 2005-10-15 |  | Lisa Legras / Lisa Bilbrey
6 | Logistics | Defined responsibility being debated on returnable packaging. We have submitted alternative packaging until this is established | Scott Barko to work with Lear to resolve issue | 2005-10-18 |  | Scott Barko