## Open issues
APQP OPEN ISSUES | [5 empty] | Form Rev 01/02/02
SUPPLIER: |  | Windsor Machine |  | DISTRIBUTION:
PROGRAM: |  | GMX272 |  | Scott Barko / Lisa Legras / Jason Vermeiren / Dick St.Pierre / Lisa Bilbrey / Phil Bryan / Phil Fairley /Todd Van Hal / Ken DeCook
COMMODITY |  | Headrest
SUPPLIER QUALITY ENG.: |  | Ken Decook
ISSUE # | ISSUE DESCRIPTION |  | ACTION PLAN | SUPPLIER/ CUSTOMER ASSIGNEE | OPEN ISSUE DATE | EXPECTED COMPLETION DATE | ACTUAL COMPLETION DATE | STATUS O = OPEN C = CLOSED | Comments
1 | Use Of Approved Leather Cleaners |  | Investigate to see if there are any approved leather cleaners. Ken feels the a product called " Simple Green " is approved however he needs to confirm and get back to Jason V. | Ken DeCook | 2005-03-04 |  |  | O
2 | Topper pad does not adhere to foam bun very well |  | Investigate if the mold release has any impact on the adhesion of the topper pad. Work with H.R. Technologies to find a better glue. | Todd Van Hal | 2005-03-04 | 2005-03-18 | 2005-03-15 | O | Met with H.R. Technologies and discussed other adhesive possibilities. Hank Augustyn to get back with WMG
3 | Assembly fixture for topper pad |  | Build and develop a assembly aid for topper pad | WMG | 2005-03-04 | 2005-04-25 |  | O
4 | Review JCI's assembly process to understand what they might subject our headrest to. |  | Visit JCI to see their process. | Todd Van Hal | 2005-03-04 | 2005-03-18 |  | O
5 | Visit Lear Mason to review GMX295/320 process |  | Arrange and visit to Lear Mason | Jason V / Todd V.H. | 2005-03-04 | 2005-03-10 | 2005-03-10 | C | Visited Lear Mason on 3/10/05 Obtained a sample of velcro and reviewed assembly process.
6 | Error proofing assembly line so that a GMX295 frame can't get built into a GMX272 mech. And vise versa. |  | Build error proofing into the assembly line. | Jake / Lisa L. | 2005-03-04 | 2005-03-31 |  | O
7 | John Bizon to visit Konel and review foam process |  | Schedule a meeting | Ken DeCook / Phil B. | 2005-03-04 |  |  | O
8 | Understand leather acceptance criteria |  | Set up meeting with Eagle Ottawa / JCI / Lear / ACSI and WMG. Ken to provide leather standards | Scott Barko / Ken DeCook | 2005-03-04 |  |  | O
9 | Identify SC/CC's for GMX272 |  | Review with Evan and establish SC/CC's | Todd Van Hal | 2005-03-04 | 2005-03-15 | 2005-03-15 | C | CRM Form e-mailed to Ken DeCook on 3/15/05
10 | Use of steam towers |  | Update current work instructions to include the use of steam towers | Jason V. | 2005-03-04 | 2005-03-18 |  | O
11 | GP12 Containment area needed |  | Set up GP12 containment area in by new foam line | Lisa L. Dick ST. | 2005-03-04 |  |  | O
12 | Caged Non Conforming Area / More space may be needed |  | Better identify product in non conforming area | Jason V. | 2005-03-04 | 2005-03-18 |  | O
13 | DFMEA for GMX272 |  | Request a copy of the DFMEA from Paul Geragosian | Todd Van Hal | 2005-03-04 | 2005-03-21 |  | O | E-mail sent to Paul Geragosian requesting a copy of DFMEA on 3/12/05
14 | Chemical Inspection |  | Get DOW to train our employees. | Phil Bryan | 2005-03-04 | 2005-04-29 |  | O | Receiving chemical inspection to be simplified to reactivity test only. Control Plan, Process Flow and FMEA to be updated by 3/18/05
15 | Qualified personnel to perform foam and chemical inspections |  | May need to hire qualified personnel | Lisa L. / Phil B. /Jason V. | 2005-03-04 | 2005-04-29 |  | O | Phil Bryan to qualify existing staff at Centroy
16 | Controlled lab to perform foam and chemical testing |  | Build a lab | Phil B. / Lisa L. / Dick St. | 2005-03-04 | 2005-04-22 |  | O | Lab to be constructed adjacent to rear restroom area for ease of access to existing utilities.
17 | Current receiving area too small |  | Designate a % of new warehouse to be a receiving area | Lisa L. / Jason V. / Dick St. | 2005-03-04 |  |  | O