## BOM & Change log
1/16/2007 lisa bilbrey |  |  | 71097-0C030 ~ 60% PWR - Mechanism & Foam Bun Asm | 71097-0C050~ 40% PWR - Mechanism & Foam Bun Asm | 71097-0C040~ 40& 60% Manual - Mechanism & Foam Bun Asm | OPEN ECR's | TMI ECI# 383WPC0164 issued date27sept06 Rec'd 05oct06 | Notes for TMI ECI # 383WPC0164 | TMI ECI# 383WPC0176 Issued date 23oct06 / Rec'd 21dec06 | Notes for TMI ECI #383WPC0176 | 200LV3903 Request for samples with grease 11-28-06 | Notes for 200LV3903 | TMI ECI# 383WPC0203 Issued: 14DEC06 | Notes for TMI ECI # ECI 383WPC0203 | TMI ECI# 383WPC0208 Issued: 21DEC06 Rec'd 02jan07 | Notes for TMI ECI # ECI 383WPC0208 | ECI 383WAF0150 Rec'd 12jan07NEED TMI ECI # | Notes for ECI# 383WAF0150
[8 empty] | Production Tool Kick off Level: Same As: Toyota ECI# Change 383WAF0128~ 28SEPT06- (ECI Lists Mechanism ASM part level information but not Mechanism and Foam Asm part level) Stamping flanges reduced, projections and embosses removed, 2 Wave washers added, Bolt longer due to added wave washers, Weld Location Changed on upper tube insert to side stampings |  | Same As: Toyota ECI# Change 383WAF0130 18DEC06 ~ Gear Change to match knob, Number of teeth reduced from 16 to 10 teeth. ECI Lists the gear shaft component part level change but no Mechanism ASM or Mechanism & Foam ASM part level change |  | Only Prototype Request Need ECI #'s ~ Adding Grease btn spring and upper tube insert interface. Listed on ECI # 383WAF0150 |  | Same As: Toyota ECI# 383WP0406 ~ (Includes a repeat of TMI ECI# 383WPC0164 and 383WPC0176) Does not list: foam rear bun and front bun part numbers with new levels, Does, Only Shows Mechanism Asm Foam Pad/ Mechanism ASM part numbers |  | Same As: Toyota ECI# 383WP0580 ~ Stay change shown but component part number not listed on ECI only the Mechanism Asm and Foam Pad Asm are listed |  | Same As: Toyota ECI# 's383WAF0150 {also listed on ECI are: 383WP0580, 0406, 0027, 0018} ~ (Somehow the Foam and Mechanism ASM part levels went back a level) Includes component part number and revisions for the post and foam changes & ADDITION OF GREASE BETWEEN SPRING AND UPPER TUBE INSERT
1 | 71943-X7C00 | INSERT, RR SEAT HEADREST | 1 | 1 | 1
2 | 71959-X7C00 | HOLDER, RRSEAT HEADREST (side stampings) | 2 | 2 | 1 | ECR008 | X "C" level
3 | 71977-X7C00 | SHAFT, RR SEAT HEADREST | 1 | 1 | 1
4 | 71949-X7C00 | HOOK, RR SEAT HEADREST | 1 | 1 | 1 | ECR002
5 | 74917-X7C00 | STOPPER, BRACKET SIDE GUARD | 1 | 1 | 1
6 | 72989-X7C00 | PLATE, RR SEAT TURN LOCK | 1 | 1 | NA | ECR005
7 | 96160-00500 | RING, SHAFT SNAP | 2 | 2 | 1
8 | 71971-X7C00 | BRACKET, RR SEAT HEADREST, RH | 1 | 1 | 1
9 | 71972-X7C00 | BRACKET, RR SEAT HEADREST, LH | 1 | 1 | 1
10 | 71331-X7C00 | PIN, RR SEAT HINGE | 1 | 1 | NA
11 | 71367-X7C00 | LINK, RR SEAT STAY, UPR RH | 1 | 1 | NA | ECR006
12 | 79298-X7C00 | SPRING, NO. 2 SEAT BACK NO. 2 | 1 | 1 | NA
13 | 71983-X7C00 | GUIDE, RR SEAT HEADREST | 1 | 1 | 1 | ECR004
14 | 71945-X7C00 | PLATE, RR SEAT HEADREST GUIDE | 1 | 1 | 1 | ECR003
15 | 72702-X7C00 | BOLT, SEAT SET | 2 | 2 | 1 |  | X "B" Level
16 | 89978-X7C02 | WASHER | 2 | 2 | 1
17 | 90179-06208 | NUT | 2 | 2 | 2
18 | 71463-X7C00 | SPRING, NO. 2 SEAT BACK | 1 | 1 | 1 | ECR009
19 | 71941-X7C01 | STAY, RR SEAT HEADREST (slave) | 1 | 1 | 1 | ECR007 | [8 empty] | X |  | "A" level
20 | 71941-X7C00 | STAY, RR SEAT HEADREST (master, cable post) | 1 | 1 | 1 | ECR007 | [8 empty] | X |  | "B" level
21 | 79939-60030 | PIN, SEAT HINGE | 1 | 1 | 1
22 | 71979-X7C00 | SHAFT, RR SEAT HEADREST, NO. 2 | 1 | 1 | 1 |  |  |  | X "A" Level
23 | 71971-X7C01 | BRKT, RR SEAT HEADREST | 1 | 1 | 1
24 | 71987-X7C00 | CABLE, RR SEAT HEADREST (long) | 1 | NA | NA
25 | 71987-X7C01 | CABLE, RR SEAT HEADREST (short) | NA | 1 | NA
26 | 90206-1009 | WASHER, WAVE | 2 | 2 | 2 |  | Level "2" New Adoption
27 | 71953-XC00 | Foam Pad Front | 1 | 1 | 1 | [11 empty] | "B" level
28 | 71953-XC01 | Foam Pad Rear | 1 | 1 | 1 | [11 empty] | "B" level
29 | 71944-X7C00 | Front Cover | 1 | 1 | 1
30 | 71944-X7C01 | Rear Cover | 1 | 1 | 1
ASM PN: | 71907-0C010 | 60% PWR - Mechanism Asm | 1 | NA | NA | ECR001 | X "C" level | [5 empty] | X "C" level |  | X "D" level |  | X "D" level
| 71907-0C030 | 40% PWR - Mechanism Asm | NA | 1 | NA | ECR001 | X "B" level | [5 empty] | X "B" level |  | X "C" level |  | X "C" level
| 71907-0C020 | 40& 60% Manual - Mechanism Asm | NA | NA | 1 | ECR001 | X "B" level | [5 empty] | X "B" level |  | X "C" level |  | X "C" level
| 71097-0C040 | 40& 60% Manual - Mechanism & Foam Bun Asm |  |  |  | ECR001 | [6 empty] | X "A" level |  | X "B" level |  | X "A" level
| 71097-0C030 | 60% PWR - Mechanism & Foam Bun Asm |  |  |  | ECR001 | [6 empty] | X "A" level |  | X "B" level |  | X "A" level
| 71097-0C050 | 40% PWR - Mechanism & Foam Bun Asm |  |  |  | ECR001 | [6 empty] | X "A" level |  | X "B" level |  | X "A" level