## PMS
JVD Open Issues List
Last Updated 6/6/06
Issue # | Issue | Actions Required | Responsible | Due Date | Status | Comments
1 | Lock pawl electric hand tool | Complete hand tool and implement at JVD | PMS | 2006-07-06 | Open | Hand tool is at JVD still needs to be developed
2 | Grease dabber for 2nd and 3rd row lock lever. | Aquire grease applicator and implement at JVD | PMS | 6/26/06 | Open | Material has been ordered.
3 | Lock pawl pivot pin press for 2nd and 3rd row | Implement at JVD | PMS | 6/13/06 | Open | Material ordered, waiting for controls
4 | 3rd row post rivetor " Prox " | Rivetor needs to be looked at, sometimes you can't get it to go to cycle. | PMS | 2006-07-06 | Open | Glen to look at rivetor
5 | Check 2nd row rivetor for anti repeat | Check PLC for anti repeat in program | PMS | 2006-07-06 | Open | Glen to look at rivetor / change to light curtain
6 | Rotary hytrel flaring machine | Build and implement at JVD | PMS | 2006-10-07 | Open | Paul D. heading up
7 | 2nd row rivetor can be cycled with missing or incorrectly orientated spring / stake | Error proof rivetor | PMS | 2006-07-06 | Open | Error proofing was removed when at Centroy. Glen to reinstall error proofing
8 | JVD requires repeatable means of measuring return / release efforts and chuck | Finish return / release and chuck fixtures and implement at JVD | Ellis / PMS | 6/20/06 | Open | Luke B. to order materials and get operational
9 | Weld flash on 3rd row lock lever causes the lever to bind up on stamping | Have a small batch of lock levers vibed to see if it resolves issue | PMS / JVD | 2006-07-06 | Open | JVD to get a 500pcs of lock lever non-heat treated then vibe and try welding to see if it makes any difference
10 | Stops are required for the 2nd row rotating side cover fixture | Call Paul D. for design and then install stops | JVD / PMS | 2006-06-06 | Closed | JVD implemented stops.
11 | Operators find it difficult to load the 3rd row lock lever spring | Develop tool to load spring | PMS | 2006-09-06 | Open | Paul D. to design and have built
10 | Operators find it difficult to load the cables to the cable anchors | Design and build a operator friendly hand tool | PMS | 2006-08-06 | Open | Paul D. / Glen S. to design and build

## Ellis
JVD Open Issues List
Last Updated 6/6/06
Issue # | Issue | Actions Required | Responsible | Due Date | Status | Comments
2 | It's difficult to remove parts from weld fixtures | make weld fixtures operator friendly | Ellis | 2006-07-06 | Open | Mark L. to have someone from Ellis look at fixtures
3 | Some weld fixtures are not at latest level | Update all weld fixtures to latest level | Ellis | 2006-07-06 | Open | Ellis to update all fixtures
4 | Some inspection fixtures are not to latest level | Ensure that all check fixtures are at the latest level | Ellis | 2006-08-06 | Open | PhilF. To verify fixtures
5 | Receiving fixtures are required for all components | Design and build receiving fixtures | Ellis | 2006-07-06 | Open | Jim to provide list of fixtures required to Steve M. Steve to have fixtures added to the tool list.
6 | Magazine feed on 3rd row tube bender does not work properly | Get magazine feed working properly and safely | Ellis | 2006-08-06 | Open | Chris F. and Glen S. to look at machine and get operating properly
8 | Difficult to load 3rd row parts in rivetor because of lock lever | Install lock lever retainer in current rivetor | Ellis | 2006-07-06 | Open | mark L. to have installed in current rivetor
9 | Difficult to load 3rd row dump spring | Design and build a devise to load dump spring ( similar to 2nd row ) | Ellis | 2006-08-06 | Open | Mark L. to design fixture and get to the floor.
12 | Need 2nd row shell attachment fixture. | Finish building and implement at JVD ( must not have spring loaded notch locators ) Must have cable locator. Needs to be set at an angle to aid the operator. A block made to the same angle as the fixture is required for the screw gun to ensure the screws are going in square. | Ellis | 2006-08-06 | Open | Mark Little
13 | tables and fixtures required for cycling the parts | Design and build cycle machine | Ellis / Lionel |  | Open | 3rd row to be the priority for the design and build

## JVD
JVD Open Issues List
Last Updated 6/6/06
Issue # | Issue | Actions Required | Responsible | Due Date | Status | Comments
1 | Needle or applicator to apply grease on 3rd row inertia stamping | Aquire grease applicator and implement at JVD | JVD | 2006-08-06 | Open | Glen to provide a devise
2 | Racks at welders for components | Build and implement racks to hold components at welders | JVD | 2006-09-06 | Open | Dick S. / Jim VD to have built
3 | Slide rack for 3rd row tubes to feed to welder | Build and implement slide rack to feed tubes to welder | JVD | 2006-09-06 | Open | Dick S. / Jim VD to have built
4 | Parts failed cut and etch testing at bodycote | Get parts to pass weld cut and etch test | JVD | 6/13/06 | Open | Dan to send new samples out to be tested that are of the latest pedegree
5 | Tables required for the welders to hold fixtures, components etc. | Build tables for welders | JVD | 2006-09-06 | Open | Dick S. / Jim VD to have built
6 | Slide rails don't fit between assembly tables | Cut rails down to size | JVD | 2006-09-06 | Open | Kyle / Jim to have rails cut down
7 | 2nd row spring loading fixture doesn't work all of the time. | Replace current shoulder bolt with a longer shoulder bolt so that it doesn't bid up. | JVD | 2006-08-06 | Open | Mark C. to install new shoulder bolt
8 | 2nd row tube fixture may not be at latest rev, | Verify fixture is at latest level | JVD | June 5 2006 | Closed | Fixture verified to be at latest revision level.
9 | Cross wire is not held secure in weld fixtures. | Verify that cross wire is being held secure in new design of fixtures | JVD | 2006-08-06 | Open | Phil B. to evaluate at Ellis tool with fixture currently at Ellis
10 | 3rd row cable anchor does not stay on fixture | Verify the angle of the anchor | JVD | 2006-08-06 | Open | Glen S. to look at weld fixtures
11 | Effort bracket does not sit securely in the weld fixture | Verify that the effort bracket sits securely in the latest design of weld fixture | JVD | 2006-08-06 | Open | Kyle to verify in fixture
12 | Rivet adjustment dials come loose | add a set screw or jamn nut to the rivetors so they don't come loose | JVD | 2006-08-06 | Open | Glen S. / Kyle L. to look at rivetors
13 | Palm buttons on 3rd row lock lever rivetor are to far apart. | Move palm buttons closer to make more erganomically friendly | JVD | 2006-08-06 | Open | Mark C. to move closer
14 | Repairs have been made to 3rd row shaft rivetor | Validate the repairs that have been made. | JVD | 2006-07-06 | Open | Kyle to validate
15 | 3rd Tape location fixture | implement and validate at JVD | JVD | June 5 2006 | Closed | Fixture validated and implemented
16 | 3rd row inertia spring needs to be orientated in assembly | Check with supplier to see if they can make the spring symetrical | JVD | 2006-08-06 | Open | Mark L. / Todd to check with supplier to see if they can accomidate this request
17 | Tape gets jambed in the tape machines | Have supplier come in and look at tape machines | JVD | 2006-09-06 | Open | Phil B. to contact supplier and have them come back in.
18 | Job duties are not very clear for each station. | Verify job duties, place pictures and visual aids at each station | JVD | 2006-08-06 | Open | Dan / Barry to update and post at each station
19 | Shell fixture needs to be moved | Move shell fixture | JVD | 2006-07-06 | Closed | Shell fixture has been relocated
21 | Go / Nogo fixture required for rivet diameters | Have fixtures designed and built | JVD | 2006-07-06 | Open | Jim to order from Coxin
22 | Sticker guns required for traceability | Purchase sticker guns | JVD | 2006-07-06 | Open | Melissa to order sticker guns
23 | Packaging is not defined | Define packaging and get into system | JVD | June 5 2006 | Closed | 10,000 boxes ordered from Smurfit
24 | Weld flash on 3rd row lock lever causes the lever to bind up on stamping | Have a small batch of lock levers vibed to see if it resolves issue | PMS / JVD | 2006-07-06 | Open | JVD to get a 500pcs of lock lever non-heat treated then vibe and try welding to see if it makes any difference
25 | No set supplier for phosing of the lock lever. | Coatings 85 has been phosing the current parts, obtain a production quote | JVD | 2006-08-06 | Open | Jim to work with Steve M. on getting a quote from Coatings 85
26 | Rack needed for presenting parts to 2nd row rivetor | Place rotary table at the line | JVD | June 5 2006 | Closed | Rotary Table has been installed
27 | Screw guns are not supposed to be oiled | Once air dryer is operating drain the oil out of the bottles that run the screw guns. | JVD | 2006-10-06 | Open | Air Dryer to be installed by 6/10/06
28 | Stops are required for the 2nd row rotating side cover fixture | Call Paul D. for design and then install stops | JVD / PMS | June 6 2006 | Closed | Stops have been installed
29 | Cables are hard to lock into the side covers | Purchase small rubber mallets. | JVD | 2006-07-06 | Closed | Mallets have been ordered
30 | Air fed screw gun | Check with Phil B. to find out the status of the screw gun | JVD | 2006-08-06 | Open | Screw gun is at WMPI waiting to come to JVD
31 | New shelving inserts on assembly tables have a sharp edge | Deburr all edges on new shelves | JVD | June 5 2006 | Closed | All inserts have been deburred
32 | EDI training required at JVD | Have Mike G. come out and provide training | JVD | 6/15/06 | Open
33 | More shelving and racks are required | Have racks built | JVD | 2006-09-06 | Open | Dick S. to have racks built
34 | Current shelving needs to be identified with what is to be used for | Label Shelving | JVD | 2006-08-06 | Open | Kyle to label shelving
35 | Weld testing procedure is needed at JVD | Develop and implement a test procedure ( Paxit Software ) | JVD / Phil F. / Phil B. | 2006-08-06 | Open | JVD / Phil B to establish a procedure and institute
36 | Cell phones still not working properly in plant | Have Kelcom provide a quote to install a 2nd repeater. | JVD | 2006-09-06 | Open | Kelcom to come in and provide a quote
37 | Permanent materials manager is required at JVD | Hire a materials manager | JVD | 06/15/06 | Open
38 | Dan and Devyn need training on tracability system | Send Dan and Devyn to Centroy to get training on their system | JVD | 06/15/06 | Open | Dan and Devan to go to Centroy
39 | Tool room needs to be set up | Set up tool room | JVD | 2006-09-06 | Open | Jim to have tool room set up
40 | Scrap pails needed for JVD | Purchase scrap pails | JVD | 2006-08-06 | Open | Scrap pails to be purchased and implemented
41 | Floor Plan Needs Updating | JVD to mark up floor plan and provide to Ellis for drawing changes | JVD / Ellis | 06/13/06 | Open | When changes are needed they are to be communicated to Ellis.