## 2nd
|  |  | 2R and 3R PIP Engineering Open Issues List | [12 empty] | Customer
| Program Name: | U222/8 CP Issues List | U222/8Engineering H/R Open Issues Build List |  |  | General:
| Customer: | Ford | Ford
| Model Yr. | 2007 | 2007-U222
| Product: | 2R and 3R seats | 2R and 3R PIP H/R
| Program #: | 222680 | 100683
| Program Mgr. | Dan Laflamme | Sharon Dodson
| Engineer. | Dan Laflamme | Sean Riley
Tracking # | Priority (A, B, C, Closed) | Customer or Internal | Problem Statement | Root Cause | Corrective Action short term/ EPT | Corrective Action long term(1PP) | Open Date | Who/When | % Comp | DA/ECR/Concern # | Detailed Plan to Closure | EPT2/1PP EVAL | Packaging | Line Side Storage/Racking etc | Process Flow
1 | A |  | Non-functioning 3rd Row head rest mechanism(10 parts of EPT lot)(SAFETY ISSUE IF FUNCTION IS MARGINAL) | Lock-tight applied to the actuating pin is "leaking" on to cam pivot. | 1.)Sort 100% for issue | 1.)Sort 100% for issue(1PP) 2.)Production intent is to projection weld. | 2006-02-22 | Windsor-Bilbrey 3-12 |  | Quality | 8D from Windsor asap
[5 empty] | 2. Function test 100% | 2.)Production intent is to projection weld. | 2006-02-22
2 | A |  | 3rd Row head rest housing's disengaging popping apart) during functioning(95%) of parts | 1.)Spring stake attachment on pivot rod interfering with housing during cycling 2.)Mounting Locations of Housing not to print causing twist in Housings. | 1.)Staple housing together(EPT) 2.)Grind stake height to match desing condition(1PP) | Modifiy stake height to match dwg/Rotate Stake 90 deg-Optimize tuning snaps for better retention(Implement 1PP) | 2006-02-22 | Windsor-Bilbrey 4/5 |  | DA-2038734 ECR-2038803 Con-C11873042 | 1.)Measure pull off force before and after change(8)-R.Leach4-10 2.)Windsor to inspect mounting surfaces and create effort vs angularity curve-Mark 4-12 | 31 PARTS Windsor owes layout data for Housing mounting
3 | A |  | 2nd Row head rest mechanism interfering with 2nd row housing during cycling. | 1.)Spring and stake attachment on pivot rod interfering with housing during cycling | Cycle parts to clear plastic at interference area. | Modifiy stake height to match dwg | 2006-02-22 |  |  | Quality | 8D from Windsor asap
4 | A |  | 3rd Row head rest strap detaching from mech.(10 parts of EPT lot). | No positive attachment of release strap to mechanism | 1.)Sort 100% for issue 2.)Verify strap is present prior to Bezel installation | Positive attachment of strap to mech(already implemented on Remainder of EPT) | 2006-02-22 | Windsor-Bilbrey 3-12 |  | Quality | 8D from Windsor asap
5 | A |  | Housing breaking during shipment(8 non-usable/100% damaged) | Shipping method allows rods to contact plastic housing | 1.)Sort 100% for issue 2.)Reject housings with holes from shipping damage | Production shipping dunnage to prevent contact between housing and rods | 2006-02-22 | Windsor-Bilbrey 3-12 |  | Quality | 8D from Windsor asap
6 | A |  | White colored Hytrel visible creating poor appearance on 3rd row head rest | 1.)TBD | 1.)Color Hytrel black with marker | 1.)Part to be colored black for production | 2006-02-22 |  |  | Quality | 8D from Windsor asap
7 | A |  | 2nd Row Cable attachment only partially attached to mechanism(3 of EPT lot) | Improper assy of cable coduit to mechanism | 1.)Sort 100% for issue 2.)Rejected parts | Verify ODS sheets at Windsor | 2006-02-22 | Windsor-Bilbrey 3-12 |  | Quality | 8D from Windsor asap
8 | A |  | Folding torque of 2nd Row head rest mech is inconsistent | None found | none required based on data-re-evaluated w/ new bezel | none required based on data-re-evaluated w/ new bezel |  |  |  | Quality | Root Cause and verification of issue complete
9 | A+ |  | Visible Gap between bezel and sto creating "no-ship" condition for 2nd Row Vinly/leather(cloth marginal)Head Rest(70% of parts) | 1.)Locating/Tuning Rib on front of bezel not optomize for build/material variation 2.)Inconsistent gap between bezel and housing at radius. | 1.)3/16 by 3/8 Foam adhesive tape(weather strip-Home Depot) applied to 100% of housing to eliminate gap to bezel. | 1.)Add .5mm to tuning rib and add radius to eliminate stress point. (1-23 White board) 2.)Modification of radius of housing to eliminate gap.(1-23 White board) 3.)Investigate glass filled polypro to optimize stiffness and dimensional stability | 2006-02-22 | Flight/Zaharia 3-12-06 |  | DA- 2038749 ECR-2038788 Con-xxtbd | Timing and cost to be completed by 12:00 am on 3-1-06
10 | A+ |  | 2nd Row head rest non-deploying if Sanoprene collapses) | 1.)Angle of interface between Rod and bezel sanoprene leading edge can cause sanoprene to collapse causing excessive friction. 2.)Thickness of sanoprene causing excessive friction to H/R Rod. | Create set in sanoprene to allow rods to open sanoprene | 1.)Modify die-direction and lead in area to more closely represent DV parts. 2.)Decrease sanoprene to DV measured parts(1.3mm)(1-23 White board) | 2006-02-22 | Flight/Zaharia 3-12-06 |  | DA- ECR-2038788 Con-xxtbd | Timing and cost to be completed by 12:00 am on 3-1-06
11 | A+ |  | 2nd Row bezels popping off when foam penetrates under bezel | 1.)Build variation can cause mis-alignment of trim cover which creates potential foam leakage | 1.)100% inspection for proper alignment 2.)Increase "hoop" sectional area to provide increased bezel retention | 1.)ODS/training for proper trim to bezel interface 2.)Increase "hoop" sectional area to provide increased bezel retention(1-23 White board) | 2006-02-22 | Flight/Zaharia 3-12-06 |  | DA- ECR-2038788 Con-xxtbd | Timing and cost to be completed by 12:00 am on 3-1-06
12 | A+ |  | 3rd row bezel difficult clip engagement when applied to trimmed part(5min takt time) | 1.)Trim cover Salvage build up in rear corner to bezel(magnified on vinyl) 2.)Perimeter snap ledge of housing creates opposing pressure on bezel during installation 3.)trim cover to bezel interference creates opposing pressure on bezel during bezel installation | 1.)Cut trim salvage to reduce stack up 2.)Remove perimeter snap ledge 3.)Increase cut-outs on trim cover | 1.Evaluate )Salvage trimming vs addition of salvage trench in housing.(Housing modification not containable for 1PP) 2.)Move perimeter overlap snap away from bezel to reduce trim cover compression(1-23 White board) 3.)Modify trim patterns to reduce bezel tension. 4.)Extend locating tabs maximum feasible distance(3mm per Kimpon-3-10) 5.)Optimize tuning Ribs for better retention(IPP) 6.)Modification of fixture to eliminate chasing of bezel when pressure applied(send fixture to saltillo 4/5)1PP implement | 2006-02-22 | Flight/Zaharia 3-12-06 |  | DA-2038734 ECR-2038803 Con-C11873042 | Sending solid fixture Saltillo Sean-4-7 | Sending
13 | A+ |  | Gap between bezel and sto on 3rd row head rest at rear | 1.)No supporting structure for trim cover | 1.)Stapling of plastic to housing(20x65) | 1. 1d-Secondary Piece(plug style) | 2006-02-22 | Flight/Zaharia 3-12-06 |  | DA-2038734 ECR-2038803 Con-C11873042 | Timing and cost to be completed by 12:00 am on 3-1-06
14 | A |  | Color Inconsistent on 2nd Row Bezels | Siloxane additive creates"swirl" appearance on bezels finish | TBD | Change siloxane carrier to be included in the plastic pellets will improve condition | TBD | TBD | TBD | Quality | TBD
15 | A |  | Sanoprene has tendency to Detach(peel back) from bezel | Siloxane additive decrease adhesion to first shot(pp) | TBD | Change siloxane carrier to be included in the plastic pellets | TBD | TBD | TBD | Quality | TBD
16 |  |  | Stapling of 3rd row trim cover creates poor takt time and potential operator safety issue] | insufficient clearance between bezel locating tab and housing | Additon of velcro to attach trim cover | Additon of velcro to attach trim cover | TBD | Chopson/Riley | 100% | 2069162 | TBD
17 |  |  | BSR-HOUSING TO FRAME on 2nd Row | Overloaded mechanism | Part Replacement | tbd | 2006-04-03 | Windsor-4-3-06 |  |  | 1.)Update with new root cause M.Little 4-7COB 2.)Provide c/m 4-7-06 | 1 part found
18 |  |  | BSR-HOUSING TO FRAME on 3rd Row | Eyelet of release strap steel on steel causing buzzing sound in head rest dumped position(currently no requirement to BSR seat in dumped postion) | Replace | Replace Eyelet with laser/Burned hole | 2006-04-01 | Vanhal-4-7 |  | DA-TBD ECR-TBD Con-TBD | 1.)Validated 4 sample at Bridgewater(M.Little4-5) 2.)Update drawing and release | able to turn issue on and off on BSR table
19 | B |  | ILD out of Spec | Spec incorrect-Data collected based off of parts that do not have plastic shells | Ship to DA | Collect data and propose new spec | 2006-02-22 | Waelde/Kerr (3-12) |  |  | Lucy to update proposal plan 4-10 | Saltillo provided Data.PIP group to propose new spec to Sean Riley
20 | B |  | 2nd Row release and return efforts out of spec | TBD | Ship to DA | Collect data and propose new spec on Return-Root Cause under way for Release effort | 2006-02-22 | Waelde/Kerr (3-12) |  |  | DA Written 3-7-06-JCI to propose new spec for return effort | EPT2 eval OK
21 | B |  | Trim Flap attachments visible on 3rd Row Head Rest creating poor appearance from rear | Plus pad is white which magnigies visibility | 1.)Color plus pad black with marker | Added radius to both coners of trim edges to reduce visibility | 2006-02-22 | Waelde/BeldingRiley 3-12 |  | DA-2040137 | 1PP implementation
22 | A |  | Wrinkles on 2nd Row head rest outside side facing | TBD | TBD | TBD | 2006-02-22 | Waelde/BeldingRiley 3-12 |  | DA-2040137 | Lucy/Waelde update 4-10 | EPT2 improved Tbd-validate on larger sample size
23 | A |  | Poor appearance around 3rd row pour hole | TBD | TBD | TBD | 2006-02-22 | Waelde/BeldingRiley 3-12 |  | DA-2040137 | TBD | EPT2 improved Tbd-validate on larger sample size
24 | A |  | "Wavy" appearance on lower front of 2nd Row head rest | TBD | TBD | TBD | 2006-02-22 | Waelde/BeldingRiley 3-12 |  | DA-2040137 | TBD | Tbd-validate on larger sample size
25 | A |  | "Wavy Welt" on 2nd Row Head Rest | TBD | TBD | TBD | 2006-02-22 | Waelde/BeldingRiley 3-12 |  | DA-2040137 | TBD | EPT 2 lev. Improved. Must compare against limit samples that do not exist and/or replace leather w/ vinyl
26 | A |  | Visible foam at 2nd Row pour opening(Aims issue 2804754) | Cover tension between bezels inadequate | apply swatch of material to pour opening | Apply 3rd row pour hole design | 2006-02-22 | Waelde/BeldingRiley 3-12 |  | DA-2040137 | Implement long-term solution @ 1PP
27 | A |  | Screw on headrest mech which holds cable mounting bracket not fully installed | TBD | TBD | TBD | 2006-03-22 | Murray/Windsor Machine |  | DA-2040137 | Implement long-term solution @ 1PP
28 | A |  | Filler cap has potential to not be assembled to 3rd Row headrest mechanism | Assembly is current operator dependent | 100% inspection | Impact study between assembly locations | 2006-03-18 | tbd | tbd | tbd | 1.)JCI to send PCR to Windsor,Saltillo,Flight G.Brown | Waiting for PCR Data from Saltillo/Windsor Machine
29 | A |  | Non-Functioning 3rd Row Mech | return spring from inertia lock not present causing mech to lock closed | 100% inspection | Sensor for spring presence to be added at Windsor Machine | tbd | tbd | tbd | tbd | tbd
30 | B |  | 2nd Row Headrest does not lock | Strap twists from contact with seat back when folding up to design position | Elastic Strap-Not preferred c/m- Requires additonal floor space and complexity | Impact study between plastic/elastic/strap c/m to determine long-term countermeasure.Ford has given direction elastic is Job 1 direction. | 2006-03-15 | Walde/Kerr/Riley | tbd | tbd | 1.)Investigate seconday plastic or redesign of Bezel for Job2 B.Zaharia/Biebel 5-1 | No issue found at EPT2(Will wait for larger sample size to close)
31 | A |  | Poor appearance of 2nd Row headrest rod | Potential lock post breakage due to hydrogen imbrittlement whidh drove mechanical plating on headrest rod | TBD | Windsor to procure pre-drawn material and replate to current mechanical plating | 2006-03-22 | tbd | tbd | tbd | 1.)Windsor to supply master sample 4-5 M.Little 2.)Run samples thru environmental chamber 4-10 S.Barko
32 | A |  | 2nd row trim cover tearing when installing mechanism into trim cover | Bezel opening to small for mechanism | increased hole size by stopping sew 10mm | increased hole size by stopping sew 10mm | tbd | 1PP | tbd | tbd | tbd | No issue at EPT2(Will wait for larger sample size to close)
33 | A |  | Salvage trimming creates increased takt time,increased risk of cutting thread and increased cost | Stack up of salvage creates poor assembly condition on 3rd row bezel | Hand trim salvage | Notch out salvage at end of pattern | tbd | 1PP | tbd | tbd | tbd | No issue at EPT2(Will wait for larger sample size to close)
34 | A |  | Head Rest dumped over railroad tracks | Excessive friction in Cam pivot(quality issue) | Measure all 1PP/FEU parts | Windsor to do 100% inspection of parts. Dimensions added to OK to ship(Investigation of assist spring to make system more robust) | 2006-04-01 | Windsor | 90% | Quality | 1.)30 piece capability on cam pivot rivet height M.Little(4-13)
35 |  |  | Button Machine(automated) inoperable | PO required for additional changes | Hand Apply buttons | utilize button machine | 2006-02-15 | Belding/Saltillo | 50% |  | 1.)
36 |  |  | 2nd Row Bezel interferes with rear of headrest rods | Bezel is allowed to migrate forward and not positively locate in design position due to gap between housing and bezel | EPT2 is improved from EPT1 | modify tuning ribs to reduce gap and limit bezel from moving forward | 2006-03-22 | Flight/Zaharia 4-8-06 | 90%
37 |  |  | Taping for BSR's both 2nd and 3rd Row headrest is not a robust design | Variation of mech and plastic | Tape | Impact study to be completed to confirm best option(tape,screws,rivet,sock) | 2006-03-22 | Murray/Riley | 90% |  | 1.)Finish design of Screw/Rivet R.Leach 4-7 2.)Windsor shipped samples of sock 4-7 3.)Create samples of Screw/Rivet(6) 4.)Investigate common screw Winters/Murray 5.)No | 1.)Finsish Design of screw 2.)Create samples of all c/m's and validate effectiveness 3.)Detailed summary and present to JCI leadership
38 |  |  | Head Rest feels very loose | TBD | ROOT CAUSE REQUIRED | ROOT CAUSE REQUIRED | 2006-03-22 | Murray/Riley/Windsor |  |  | 1.)Coorelate data to the complete headrest
39 |  |  | Production tools have not been kicked off | STO has not been verified to print | get parts scanned | Update Data to latest STO | 2006-03-22 | Murray/Riley/Kerr |  |  | 1)Write engineering req to get 8 headrests scanned Kerr/Murray/Riley4-10
40 |  |  | Several ECO's at planned ECO | Too many damn issues | complete drawings and release | complete drawings and release | 2006-03-22 | Murray/Riley/Kerr |  |  | 1.)Windsor 3rd 12:00 2.)Verify if tape is required 3.)Release drawings by 4-7 cob Murray/Riley
41 |  |  | "Popping" 3rd Row mech assy | Lisa Bilbry took part to WM @ 2:00 on 4-6-06 | 100% inspection | tbd |  |  |  |  | 1.)8D by COB 4-7-06
42 |  |  | Headrest Guide Shearing when installing into steel | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | 1.)Tolerance stack 4-10-06 Riley 2.)Evaluate intalled opening size of guide 4-11-06 Murray
43 |  |  | Can not make rate with current headrest intallation time/effort | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART | TBD-CORE PART