## CAR Form
Corrective Action Report (C.A.R.)
Pioneer Polymers, Inc.
| Customer |  |  | Supplier |  |  | Internal |  | X | TUV
Part #: |  |  | 7C34-5291-GC |  |  | C.A.R. #: | PPI-093
Part Name: |  |  | BRKT & INS ASY CONV SUPT |  |  | Issue Date: | 2008-04-10
Company: |  |  | Wayne |  |  | Issued By: | Pauline McCusker
Contact: |  |  | Beth Muse |  |  | Issued To: | Pioneer
Phone / Fax: |  |  | 734-941-7320 |  |  | Final Due: | 2008-06-11
Team: |  | Pierre Marentette, Mike Peltier, Jim Lussier, Mark Brockman
Problem Description:
Nonconformity: The process verify product requirements and react to out of control situation when found was observed as ineffective.
Weld testing: Part # 7C34-5291-GC control plan dated 3-May-07 calls for weld destruct testing to meet weld spec WA=GMAW. Evidence: There were no records available to show that this is happening.
[6 empty] | Repeat Issue | Yes | No | X
Interim Containment Actions: |  |  |  | N/A
Define & Verify Root Cause(s):
The control plan cites that a weld destruct test will be performed on this part.
After scrutinizing the blueprint, no callout for a weld destruct test or etch test could be identified.
Since there are no specifications for the weld destruct test, Pioneer will have to determine its own criteria for the test.
Implement Permanent Corrective Action(s):
The customer has not identified criteria for what is considered acceptable for the welds. Pioneer has developped its own criteria for what is to be considered as acceptable. The criteria derives from GMAW weld standard. The part will be evalutated as far as configuration, and a procedure developped. (Target June 6, 2008)
All shift supervisors are to be trained on how to use the procedure, and performing the procedure by June 9, 2008.
Verify Corrective Action(s)
To date, two weld destruct tests have been performed, and logged. Following a conversation between Mike P and Pierre M, since there is no specified criteria from the customer as to what is acceptable, and based on how we arrived to establishing our own criteria, we feel that the test is effective in determining if the weld are good, and the evidence retained would prove due diligence to our customer.
Prevent Reoccurrence: The following areas have been revised where applicable:
| FMEA |  | Control Plan | Operator Inst | X | Inspect Inst | Gauge | Gauge Inst |  | Flow
| Approved |  | Rejected | Signature: |  |  |  | Date:
Please sign and return. If no reply within 14 days this CAR will be considered closed.
Controlled Copy when in red |  |  |  | May not be latest revision if not red check with master copy